## Sheet1
THE MAIN THING
From | To | # of Pieces | # of parts | Approx Time | ppm @
Stand |  |  | approximations |  | 3 | [7 empty] | TIME LINE is Rounded to the NEXT Highest Integer
[13 empty] | ***** | Time Line
1 | 6 | 71 | 12 | 4 |  |  |  | Step 1 | Sorting |  |  |  |  | 0 | Start | ***** | For Compensating the following factors
7 | 10 | 20 | 5 | 1.6667 |  |  |  |  | E1,E2,E3,Ef | Hand radar parts to PM |  |  |  | 1.5 |  |  |  | E1 | E2 | E3 | E4 |  | Time
11 | 11 | 8 | 2 | 0.66667 |  |  | Time Taken for each task |  | 4 | [6 empty] | Manual Reading Comprehension Time |  | 2 | 2 | 2 | 2 |  | 2
12 | 15 | 48 | 7 | 2.3333 |  |  |  |  | Done |  |  |  |  | 4 | End
16 | 17 | 19 | 5 | 1.6667 | [11 empty] | Pause to Rest, Mistakes, Breakage and Rework, or tto account for Error in time estimation |  | 5 | 5 | 5 | 5 |  | 5
18 | 18 | 18 | 2 | 0.66667 |  |  |  | Step 2 | Hatch | Stand | Lander | Rover |  | 4 | Start
Total # Pieces = |  | 184 |  | 11 |  |  |  |  | E1 | E2 | E3 | Ef |  |  |  |  | Margin after each step [SLACK] | 1 | 1 | 1 | 1 | X 7 | 7
[9 empty] | 41 to 45 | 1 to 6 | 19 to 22 | 54 to 58 | [9 empty] | (7 steps) | 14
Lander | [6 empty] | Time Taken for each task |  | 5.6667 | 4 | 4.6667 | 5.3333 | 3 | 13 | End
19 | 22 | 32 | 14 | 4.6667 |  |  |  |  | Done
23 | 23 | 8 | 6 | 2
24 | 25 | 23 | 5 | 1.6667 |  |  |  | Step 3 |  | Stand | Lander | Rover |  | 13 | Start
26 | 27 | 16 | 6 | 2 |  |  |  |  | E1 | E2 | E3 | E4
28 | 29 | 10 | 5 | 1.6667 |  |  |  |  | 12 to 15 | 7 to 11 | 23 | 59 to 61
30 | 32 | 17 | 6 | 2 |  |  | Time Taken for each task |  | 2.3333 | 2.3333 | 2 | 2.3333 | 3 | 19 | End
33 | 35 | 9 | 5 | 1.6667
36 | 38 | 10 | 5 | 1.6667 |  |  |  | Step 4 | Stand | Lander |  | Rover |  | 19 | Start
39 | 40 | 21 | 5 | 1.6667 |  |  |  |  | E1 | E2 | E3 | E4
41 | 42 | 13 | 5 | 1.6667 | Hatch |  |  |  | 16 to 18 | 30 to 38 | 24 to 29 | 62 to 64
43 | 45 | 18 | 12 | 4 |  |  | Time Taken for each task |  | 2.3333 | 5.3333 | 5.3333 | 5.3333 | 3 | 28 | End
46 | 47 | 11 | 5 | 1.6667 |  |  |  |  | E1 Assists in remaining time
48 | 50 | 13 | 5 | 1.6667
51 | 53 | 11 | 4 | 1.3333 | Radar |  |  | Step 5 | Stand | Lander |  | Rover |  | 28 | Start
Total # Pieces = |  | 212 |  | 29.3333 |  |  |  |  | E1 | E2 | E3 | E4
[9 empty] | Assemble | 39 to 40 | 46 to 47 | Assemble
Rover | [6 empty] | Time Taken for each task |  | 2 | 1.6667 | 1.6667 | 2 | 1 | 31 | End
54 | 58 | 43 | 16 | 5.3333 |  |  |  |  | Done |  |  | Done
59 | 61 | 19 | 7 | 2.3333
62 | 64 | 35 | 16 | 5.3333 |  |  |  | Step 6 | Lander |  |  |  |  | 31 | Start
Total # Pieces = |  | 97 |  | 13 |  |  |  |  | E1 | E2 | E3 | E4
Assembling Parts |  |  |  | 4 |  |  |  |  | Assemble | 48 to 53, Assemble | Assemble and Assist
Sorting |  |  |  | 3.5 |  |  | Time Taken for each task |  | 3 | 3 | 3 | 3 | 2 | 36 | End
Final assembley |  |  |  | 2 |  |  |  |  | Done
Manual Comprehension |  |  |  | 3.5
Total # of Pieces |  | 493 | Initial Total Time | 42.3333 |  |  |  | Step 7 | Final Assembly (FA) and Structural Integrity Check (SIC) |  |  |  |  | 36 | Start
|  | Critical Path |  | Sort + Lander + Assembly |  |  |  |  | E1 | E2 | E3 | E4
[9 empty] | SIC | FA | SIC | FA
[7 empty] | Time Taken for each task |  | 2 | 2 | 2 | 2 | 2 | 40 | End
[6 empty] | Total Time After Entire Scheduling and Levelling | [7 empty] | 40 | Minutes